## Slide 1
Elevate core Go Live effort
JIRA tasks
Ledger
Bank Adapters
30 days
Card templates
10 days
Authentication changes 10 days
Orchestrator
Ledger changes
6 days
Completion checks 5 days
Reconciliation
Asset based postings 5 days
View-based balances 5 days
Go Live
Infrastructure
5 days
Adapters
5 days
IT Sec
5 days
Deployment
2 days
SIT
9 days
UAT
8
CMS
Support 15 days
Total effort: 120 days
Core Team resources: 75 days
Additional resources needed: 2
Start : 02/02/2026
End: 28/02/2026

## Slide 2
MT
Design 5 days
Tenant Identity Model – 5 days
Tenant-based Auth – 7 days
Tenant based schema – 20 days
Tenant isolation – 14 days
Readiness Testing 7 days
Multi-tenancy+ White-Labelling
WL
Brand Layer
UI
Comms – 6 days
Packaging – 6 days
Domain management – 10 days
Total effort: 80 days
Core Team resources: 0 days
Additional resources needed: 2
Start : 02/02/2026
End: 27/03/2026

## Slide 3
Elevate card go-live effort
Card processor integration
10 days
Card Lifecycle
40 days
Card Reconciliation
20 days
Total effort: 70 days
Additional resources required: 0 (UHF)
Start : 22/01/2026
End: 28/02/2026

## Slide 4: Go Live Book of Work – planned activities
Deliverable | Description | Layer | Status | Effort | ETC
Ledger service | Maintains the ledger | Backend | 100% | 10 | 13/03/2026
Recon service | EOD reconciliation | Backend | 90% | 10 | 24/03/2026
COP service | Confirmation of Payee service | Backend | 100% | 3 | 10/02/2026
COP in UI | COP used in user/admin portal | UI | 100% | 6 | 16/02/2026
User portal / Admin portal | Web app for users | UI | 100% | 12 | 27/02/2026
Card lifecycle – Elevate | Processing different stages of card transaction | Backend | 100% | 10 | 27/02/2026
FPMS integration - Elevate | Forwarding of daily transactions to FPMS | Backend | 100% | 10 | 27/02/2026
JIRA issues – reviewed | Issues raised by Arbab/Amandeep | UI | 100% | 10 | 27/02/2026
Automated account opening | Triggered by FPMS customer approval | Backend | 100% | 6 | 13/03/2026
Multi-tenancy – Core | Enabling different tenants using the backend services | Backend | 75% | 15 | 23/04/2026
Comprehensive Audit logs | Audit trail of user actions during a session | UI + Backend | 100% | 7 | 04/03/2026
V2 SIT deploy | New version with change request, bug fixes, usability fixes | All | 100% | 3 | 05/03/2026
Day-1 data seeding | Data seeding for Go Live Day-1 | Backend | 100% | 7 | 13/03/2026
Card lifecycle – CMS | chargeback, reversal, refund, reconciliation outstanding | CMS | 80% | 10 | 31/03/2026
UI-CMS integration | User portal integration with CMS | UI | 100% |  | 12/03/2026
UI-CMS integration | Admin portal | UI | 75% |  | 28/03/2026

## Slide 5: Go Live Book of Work – unplanned activities
Deliverable | Description | Layer | Status | ETC
Mobile App | As per Figma design | UI | 100% | 19/03/2026
System Integration Testing | End-to-end Testing with all the components | All | 100% | 27/03/2026
JIRA issues – some reviewed | High priority of ~40 Functional/Usability Issues raised | Mixed | 75% | 31/03/2026
Production infrastructure | Configuration, setup and preparation | All | 60% | 31/03/2026
Build pipeline | Build pipeline for prod setup and software installed | All | 0% | 07/04/2026
Pen Testing | Application/infrastructure security testing by 3rd party | All | 0% | 24/04/2026
Card processor integration | Integration with CLOWD9 and Visa | CMS + Core | 0% | 30/04/2026
Banking integration | Equals Money, Banking Circle, Bank of London | All | 0% | 30/04/2026
JIRA issues | Additional usability/functionality tickets | All | 0% | 30/04/2026
Go-Live pilot | Testing with selected clients, FPMS and banking partners | All | 0% | 29/05/2026
Go-Live – single tenant | Live for frontier-pay customers | All | 0% | 19/06/2026
White-labelling | Allow configurable branding by tenants | Backend + UI | 5% | 30/06/2026
Go-live date – multi tenant | Live for other EMI’s | All | 0% | 31/07/2026
Customer migration to Elevate | Migration of current Trusek customers to Elevate | Backend | 0% | 28/08/2026